## Sprint Tracker
Sprint Number | Week Number | User Story ID | User Story Description | Module | Priority | Assigned To | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Remarks
1 | 1 | US_01 | Define system objectives and success criteria | Backend | Must | Management | 2025-12-02 | 2025-12-06 | 2025-12-02 | 2025-12-06 | Completed | Clear objectives documented
1 | 1 | US_02 | Identify and document target user personas | Frontend | Must | Team Frontend | 2025-12-02 | 2025-12-06 | 2025-12-02 | 2025-12-06 | Completed | 3 user personas created
1 | 1 | US_03 | Research and evaluate NLP summarization models | AI Engine | Must | Team AI | 2025-12-02 | 2025-12-08 | 2025-12-02 | 2025-12-08 | Completed | Compared GPT-4 vs Gemini vs OpenRouter
1 | 1 | US_04 | Create comprehensive system architecture diagram | Backend | Must | Management | 2025-12-02 | 2025-12-06 | 2025-12-02 | 2025-12-06 | Completed | Architecture documented in Lucidchart
1 | 1 | US_05 | Finalize technology stack (React + Django + OpenRouter) | DevOps | Must | Management | 2025-12-04 | 2025-12-08 | 2025-12-04 | 2025-12-08 | Completed | React 19 + Django 4.2 + OpenRouter API
2 | 2 | US_06 | Setup Django backend framework with project structure | Backend | Must | Team Backend | 2025-12-09 | 2025-12-13 | 2025-12-09 | 2025-12-13 | Completed | Django 4.2.7 + DRF installed
2 | 2 | US_07 | Design and implement PostgreSQL database schema | Database | Must | Team Backend | 2025-12-09 | 2025-12-15 | 2025-12-09 | 2025-12-13 | Completed | Initially used LocalStorage approach
2 | 2 | US_08 | Design RESTful API structure and endpoints | Backend | Must | Team Backend | 2025-12-09 | 2025-12-15 | 2025-12-09 | 2025-12-13 | Completed | 5 main endpoints defined
2 | 2 | US_09 | Implement JWT authentication with user roles | Backend | Must | Team Backend | 2025-12-11 | 2025-12-15 | 2025-12-11 | 2025-12-15 | Completed | Firebase Auth integrated instead
2 | 2 | US_10 | Create file upload endpoint with validation | Backend | Must | Team Backend | 2025-12-12 | 2025-12-15 | 2025-12-12 | 2025-12-15 | Completed | Multi-format support added
3 | 3 | US_11 | Integrate PDF parsing library (pypdf/PyPDF2) | Backend | Must | Team Backend | 2025-12-16 | 2025-12-20 | 2025-12-16 | 2025-12-20 | Completed | Client-side parsing implemented
3 | 3 | US_12 | Develop robust text extraction module from PDFs | Backend | Must | Team Backend | 2025-12-16 | 2025-12-22 | 2025-12-16 | 2025-12-20 | Completed | Handles multi-page PDFs efficiently
3 | 3 | US_13 | Build text preprocessing pipeline (cleaning tokenization) | AI Engine | Must | Team AI | 2025-12-17 | 2025-12-22 | 2025-12-17 | 2025-12-22 | Completed | Text normalization implemented
3 | 3 | US_14 | Implement section segmentation (Abstract Method Results) | AI Engine | Should | Team AI | 2025-12-18 | 2025-12-22 | 2025-12-18 | 2025-12-22 | Completed | AI-based section detection
3 | 3 | US_15 | Add comprehensive error handling for PDF processing | Backend | Must | Team Backend | 2025-12-19 | 2025-12-22 | 2025-12-19 | 2025-12-22 | Completed | Graceful error messages added
4 | 4 | US_16 | Integrate OpenRouter API for LLM summarization | AI Engine | Must | Team AI | 2025-12-23 | 2025-12-27 | 2025-12-23 | 2025-12-27 | Completed | OpenRouter API fully integrated
4 | 4 | US_17 | Develop extractive summarization algorithm | AI Engine | Should | Team AI | 2025-12-23 | 2025-12-29 | 2025-12-23 | 2025-12-27 | Completed | Key sentence extraction implemented
4 | 4 | US_18 | Implement abstractive summarization using LLM | AI Engine | Must | Team AI | 2025-12-24 | 2025-12-29 | 2025-12-24 | 2025-12-29 | Completed | Structured summary generation
4 | 4 | US_19 | Build keyword and key concept extraction module | AI Engine | Should | Team AI | 2025-12-25 | 2025-12-29 | 2025-12-25 | 2025-12-29 | Completed | Technical terms identified
4 | 4 | US_20 | Evaluate and test summarization accuracy | AI Engine | Should | Team QA | 2025-12-26 | 2025-12-29 | 2025-12-26 | 2025-12-29 | Completed | 95% accuracy on test papers
5 | 5 | US_21 | Extract research objectives from papers using AI | AI Engine | Must | Team AI | 2025-12-30 | 2026-01-03 | 2025-12-30 | 2026-01-03 | Completed | Objectives section parsed
5 | 5 | US_22 | Extract and structure research methodology | AI Engine | Must | Team AI | 2025-12-30 | 2026-01-05 | 2025-12-30 | 2026-01-03 | Completed | Methodology details extracted
5 | 5 | US_23 | Extract datasets and experimental setup information | AI Engine | Should | Team AI | 2025-12-31 | 2026-01-05 | 2025-12-31 | 2026-01-05 | Completed | Dataset identification added
5 | 5 | US_24 | Extract conclusions and future work sections | AI Engine | Must | Team AI | 2026-01-01 | 2026-01-05 | 2026-01-01 | 2026-01-05 | Completed | Conclusions parsed successfully
5 | 5 | US_25 | Generate structured insight report in JSON format | Backend | Must | Team Backend | 2026-01-02 | 2026-01-05 | 2026-01-02 | 2026-01-05 | Completed | Clean JSON output format
6 | 6 | US_26 | Setup React 19 project with Vite build tool | Frontend | Must | Team Frontend | 2026-01-06 | 2026-01-10 | 2026-01-06 | 2026-01-10 | Completed | Vite 6.2 configured
6 | 6 | US_27 | Design and build PDF upload interface with drag-drop | Frontend | Must | Team Frontend | 2026-01-06 | 2026-01-12 | 2026-01-06 | 2026-01-10 | Completed | Beautiful upload UI created
6 | 6 | US_28 | Create responsive summary display panel | Frontend | Must | Team Frontend | 2026-01-07 | 2026-01-12 | 2026-01-07 | 2026-01-12 | Completed | 4-section summary view
6 | 6 | US_29 | Build interactive insight visualization cards | Frontend | Should | Team Frontend | 2026-01-08 | 2026-01-12 | 2026-01-08 | 2026-01-12 | Completed | Card-based UI with animations
6 | 6 | US_30 | Add loading animations and progress indicators | Frontend | Should | Team Frontend | 2026-01-09 | 2026-01-12 | 2026-01-09 | 2026-01-12 | Completed | Spinner and progress bars
6 | 6 | US_31 | Implement dark mode theme with Tailwind CSS | Frontend | Could | Team Frontend | 2026-01-10 | 2026-01-12 | 2026-01-10 | 2026-01-12 | Completed | Full dark mode support
7 | 7 | US_32 | Build AI Research Readiness Score evaluation | AI Engine | Must | Team AI | 2026-01-13 | 2026-01-17 | 2026-01-13 | 2026-01-17 | Completed | 5 scoring criteria implemented
7 | 7 | US_33 | Implement citation count detection from references | AI Engine | Could | Team AI | 2026-01-13 | 2026-01-19 | 2026-01-13 | 2026-01-17 | Completed | Reference parsing added
7 | 7 | US_34 | Add similar paper suggestion using semantic search | AI Engine | Could | Team AI | 2026-01-14 | 2026-01-19 | 2026-01-14 | 2026-01-19 | Completed | Semantic search implemented
7 | 7 | US_35 | Create export summary as PDF functionality | Frontend | Should | Team Frontend | 2026-01-15 | 2026-01-19 | 2026-01-15 | 2026-01-19 | Completed | jsPDF library integrated
7 | 7 | US_36 | Build analytics dashboard for user insights | Frontend | Could | Team Frontend | 2026-01-16 | 2026-01-19 | 2026-01-16 | 2026-01-19 | Completed | Dashboard tracks papers
7 | 7 | US_37 | Add multi-language chat support (EN HI MR) | AI Engine | Should | Team AI | 2026-01-17 | 2026-01-19 | 2026-01-17 | 2026-01-19 | Completed | Gemini AI for multi-language
8 | 8 | US_38 | Integrate frontend with backend API endpoints | DevOps | Must | Team DevOps | 2026-01-20 | 2026-01-24 | 2026-01-20 | 2026-01-24 | Completed | Axios HTTP client configured
8 | 8 | US_39 | Setup Docker containers for deployment | DevOps | Should | Team DevOps | 2026-01-20 | 2026-01-26 | 2026-01-20 | 2026-01-24 | Completed | Docker configuration created
8 | 8 | US_40 | Perform end-to-end performance testing | DevOps | Must | Team QA | 2026-01-21 | 2026-01-26 | 2026-01-21 | 2026-01-26 | Completed | Load testing completed
8 | 8 | US_41 | Conduct comprehensive bug fixing and QA | DevOps | Must | Team QA | 2026-01-22 | 2026-01-26 | 2026-01-22 | 2026-01-26 | Completed | Critical bugs fixed
8 | 8 | US_42 | Write technical documentation and user guide | DevOps | Must | Management | 2026-01-23 | 2026-01-26 | 2026-01-23 | 2026-01-26 | Completed | Comprehensive docs created
8 | 8 | US_43 | Deploy to production (Netlify + Render) | DevOps | Must | Team DevOps | 2026-01-24 | 2026-01-26 | 2026-01-24 | 2026-01-26 | Completed | Live at reserachinsigher.netlify.app
8 | 8 | US_44 | Final optimization and performance tuning | Backend | Should | Team Backend | 2026-01-27 | 2026-01-28 | 2026-01-27 | 2026-01-28 | Completed | API response time optimized

## Project Summary
Metric | Value
Project Title | AI Powered Research Paper Summarizer and Insight Extractor
Total Sprints | 8
Total User Stories | 44
Total Weeks | 8
Project Start Date | 2025-12-02
Project End Date | 2026-01-28
Completion Rate | 100%
On-Time Delivery Rate | 100%
Total Features Delivered | 8
Priority Distribution (MOSCOW)
Must Have | 25
Should Have | 14
Could Have | 5
Won't Have | 0
Module Distribution
Frontend | 8
Backend | 12
AI Engine | 15
DevOps | 7
Database | 2
Tools & Technologies Used
Frontend Framework | React 19.2.3
Build Tool | Vite 6.2.0
Programming Language | TypeScript 5.8.2
Styling Framework | Tailwind CSS
Backend Framework | Django 4.2.7
API Framework | Django REST Framework 3.14.0
Authentication | Firebase Auth
AI Provider | OpenRouter + Google Gemini
PDF Processing | Client-side + pypdf 3.17.1
Deployment Frontend | Netlify
Deployment Backend | Render.com
Key Features Delivered
Feature 1 | PDF Upload & Parsing (Client-side)
Feature 2 | AI-Powered Summarization (Abstract Findings Methodology Limitations)
Feature 3 | Technical Insights Extraction (Concepts Objectives Results Conclusions)
Feature 4 | Semantic Search across Documents
Feature 5 | Multi-Language AI Chat (English Hindi Marathi)
Feature 6 | Research Readiness Evaluation (5 Scoring Criteria)
Feature 7 | Voice Interaction (Speech-to-Text & Text-to-Speech)
Feature 8 | Dark/Light Theme Support
Team Composition
Product Owner | 1
Technical Architect | 1
Backend Developers | 2
Frontend Developers | 2
AI Engineers | 2
DevOps Engineers | 1
QA Engineers | 1
UI/UX Designer | 1
Success Metrics
User Adoption | Production Ready
System Uptime | 95%+
Average Response Time | < 3 seconds
User Satisfaction | High (4+ stars expected)
Test Coverage | Manual + E2E Testing
Risk Management
API Rate Limits | Mitigated with caching
Large PDF Processing | Client-side parsing approach
Backend Cold Start | User feedback on first request
Data Privacy | Client-side processing + secure auth

## Team Legend
Team Name | Description
Team Frontend | Frontend Development, UI/UX Design
Team Backend | Backend Development, Database, Security
Team AI | AI/ML Engineering, NLP, Model Integration
Team DevOps | DevOps, Infrastructure, Full-Stack
Team QA | Quality Assurance, Testing
Management | Product, Architecture, Documentation